## Sheet1
|  | Project Name: | To Do List
|  | Project Description: | A Crud Functioning web based To do List application
|  | Project Owner: | Emmanuel Lomax
Risk ID | Date registered | Risk area | Risk description | Probability |  | Risk Level |  |  | Project impact | Proximity / Length of impact | Response strategy
1 | 29.12.20 | Covid-19 Mutant Strain | Risk of illness and inability to work as effectively due to more dangerous effects of mutant strain |  | x |  | x |  | Moderate, could slow down progress but since most work done online it's possible to power through. | 2 weeks to couple of months | Take hygeine steps more throughly and order food to be delivered instead of shopping physically whenever possible.
2 | 30.12.20 | Internet Connection Interruption during Presentation | Though it rarley happens some network disruption or repairs may occur. |  | X |  |  | x | Even if I have the best files ready, which is already unlikely the presentation itself is important, making this unideal, | Couple of hours to couple of days. | I suppose a mobile hotspot could fix things but I'd have to communicate the issue effectively and there'd be gaps.
3 | 08.01.21 | Fall down the stairs and break an arm. | Having to code with one hand or even worse if both hands get broken, by dictation is a very horrid circumstance. |  | X |  |  | X | Very high impact, it could cause massive delays and stress. | Till end of project and beyond. | Set my alarm back a couple or hours when waking and set it forwards a couple hours at night. It would be a matter of making up for time lost.
#REF! | 12.01.21 | Could slip in the shower | Nearly slipped a little yesterday so this seems a valid risk. |  | X |  | X |  | Moderate to high depending if I land on my head or not. Could range between a coma and a bruise. | 1 day to end of project and beyond | Be more careful and maybe switch to baths.
#REF! | 14.01.21 | Virus and/or Hacking | My internet security is running out soon and I haven't gotten new subscription yet, due to laziness really. |  | x |  | x |  | I could have my progress not already on Github wiped out. | At least a couple of weeks. | Just update already.
#REF! | 14.01.21 | Pneumonia | It's pretty cold these days, apparently you can get pneumonia when its cold enough |  | x |  |  | x | High impact due to it's weakening effects | At least a week to a month | Keep warm and don't go outside unless necessary and when you do, wrap up warmly.
#REF!
#REF!
#REF!